Client Onboarding Process

| Document ID | OPS-001 | Version: 1.0 |
| --- | --- | --- |
| Department | Operations | June 2026 |

# 1. Purpose

This document defines the end-to-end process for onboarding new clients, from contract signature to go-live. A smooth onboarding experience is critical to client retention, satisfaction, and long-term revenue.

# 2. Onboarding Phases

| Phase | Activities | Duration | Owner |
| --- | --- | --- | --- |
| Kickoff | Intro call, stakeholder mapping, success criteria | Day 1 | Account Manager |
| Discovery | Requirements gathering, integration review | Week 1–2 | Solutions Engineer |
| Setup | Account config, data migration, user provisioning | Week 2–4 | Implementation |
| Training | Admin and end-user training sessions | Week 4–5 | Customer Success |
| Go-Live | Launch, hypercare period begins | Week 5–6 | Account Manager |
| Steady State | QBRs, health scoring, expansion | Ongoing | CSM |

# 3. Kickoff Meeting Agenda

- Introductions and team overview (15 min)

- Review of contract scope and success criteria (20 min)

- Project timeline and milestone walkthrough (15 min)

- Communication cadence and escalation path (10 min)

- Q&A and next steps (15 min)

# 4. Client Health Scoring

| Score | Status | Action |
| --- | --- | --- |
| 8–10 | Healthy | Standard QBR cadence |
| 5–7 | At Risk | Monthly check-in, action plan |
| 1–4 | Critical | Exec escalation, recovery plan |

# 5. Handoff Criteria (Implementation to CSM)

- All integrations live and tested

- Admin users trained and signed off

- Handoff call completed with documented notes

- Client satisfaction score (CSAT) collected at go-live