Client Onboarding Process v2.0

| Document ID | OPS-006 | Version: 2.0 |
| --- | --- | --- |
| Department | Operations | June 2026 |

# 1. Purpose & Version Notes

Version 2.0 introduces a redesigned 6-phase onboarding journey, AI-assisted implementation checklist, and a revised health scoring model. Average time-to-value target reduced from 6 weeks to 4 weeks. Supersedes OPS-001 v1.0.

# 2. Updated Onboarding Phases

| Phase | Activities | Target Duration | Owner |
| --- | --- | --- | --- |
| 1. Alignment | Kickoff, success criteria, exec sponsor | Day 1–2 | Account Manager |
| 2. Discovery | Requirements, integrations, data audit | Week 1 | Solutions Engineer |
| 3. Build | Config, integrations, data migration | Week 1–2 | Implementation |
| 4. Validate | UAT, edge-case testing, sign-off | Week 3 | CSM + Client |
| 5. Launch | Go-live, 2-week hypercare | Week 4 | Account Manager |
| 6. Optimise | QBRs, expansion, health scoring | Ongoing | CSM |

# 3. AI Implementation Checklist (New)

- AI auto-generates client-specific checklist from Discovery call transcript

- Each item assigned to Client or Internal with due date

- Weekly progress report auto-emailed to client stakeholders every Monday

- Blocked items flagged to Account Manager + CSM within 24 hours of becoming overdue

# 4. Revised Health Scoring Model

| Dimension | Weight | Key Signals |
| --- | --- | --- |
| Product Adoption | 30% | DAU, feature usage, login frequency |
| Relationship | 25% | NPS, responsiveness, exec engagement |
| Outcomes | 25% | Success criteria achievement rate |
| Support Health | 20% | Open tickets, CSAT, escalation count |

# 5. Time-to-Value SLA (New)

- SMB clients: go-live within 3 weeks — breach triggers CSM escalation

- Mid-market clients: go-live within 5 weeks — breach triggers VP review

- Enterprise clients: go-live within 10 weeks — milestone-based SLA tracked per contract

# 6. Change Log

| Version | Doc ID | Date | Changes |
| --- | --- | --- | --- |
| 1.0 | OPS-001 | Jan 2025 | Initial release |
| 2.0 | OPS-006 | Jun 2026 | 6-phase model, AI checklist, health scoring, TTV SLA |